## TLHP
TLHP |  | priority | status | assignment | desc | unfinish | link
| Login different app change logo & text | high
bug on user history
KKLHP bug if edit cannot add button more in a b c
| Summernote upload to file system | low
| Summernote |  | done | rudi
| Page Template Laporan | high | progress | rudi
| Log History | medium |  | agus
| Console error | high | done
hari awal tidak boleh lebih dari hari akhir
| total temuan, rekor, sesuai, belum sesuai, belum tl, tdk dpt ,tl | high
| input normal form kklhp | high
| header current App | high | done | haidar
| Header fullname | high |  | haidar
| Header, footer, logo current app | high
| Input tindak lanjut | high
| History Tindak Lanjut | high
| Create 404, error db, etc to underconstruction & 404 | high | done |  | using error/ folder and change header & footer | if php file error than bad error
| Repair User password add edit add repassword |  | done |  | require re pass if pass input in edit
| Insert Kode Sebab, Uraian, Temuan using csv | medium | progress | rudi
| User Authentication |  | done
| Bug ON after add tr rekomen / add more get from last so inputan nya masi ke bawa | medium
| total use login logout | medium
| Cetak Print | medium
| Export to Excel | medium
| Export to PDF | medium
| Create Tables for 4 app | high | done | haidar
| Create Multi App login & tables |  | done | agus
upload jquery
| kklhp add row temuan |  |  | dendi
| kklhp add row rekomendasi |  |  | dendi
| kklhp insert to db |  |  | dendi
| fitur redirect previous url | low
| Edit LHP Menu | medium |  | haidar
| call reprosess after insert / update manus datatable | low
| Add tim coding post | medium
| add tim disable double | medium
| datatable get manus |  | done
| ci tlhp |  | done
| ci dashboard |  | done
| modal for add user |  | done | agus
| modal for edit user |  | done | agus
| data table |  | done | haidar
| Electronic follow up recommendation (index.php) & RB |  | done | haidar
| index dashboard tlhp legend on pie chart for printing | medium
| footer add logo kemenpan |  | done | alfon
| print dashboard layout | medium
| menu layout addlhp fix width & height |  | done | alfon
| menu addlhpbaru tgl penugasan & skop pemeriksaan tidak dapat lebih muda dari surat tugas | medium
addlhpbaru ganti upload laporan
| addlhp all require |  | done
| kklhpbaru tambah A. Sistem, B. Kepatuhan tombol tambah | high |  | dendi
| kklhpbaru kode rekomendasi dropdown chain sub kelompok | high |  | dendi
| kklhpbaru checkbox kerugian negara | high |  | dendi
| kklhpbaru kode sebab muncul kan uriaian text nya | high |  | dendi
| tambah setelah unit kerja nama ppk & PJ Kegiatan | high |  | dendi
| kklhp tambah tombol apabila tindak lanjut | high |  | dendi
Login & choose app using same header & footer
| Bikin Button Export to Excel,pdf,print di halaman .. kklhp | high |  | alfon
| halaman laporan | high |  | alfon
| font muly download ke local |  | done | alfon
| hari penugasan perpanjangan kolum date nya tidak sama |  | done | alfon
| header make smaller |  | done | alfon
| dashboard app make like |  |  | alfon |  |  | http://demos.creative-tim.com/paper-dashboard-pro/examples/dashboard/overview.html
| bug datetime picker no hover an active date |  | done | alfon
| bug on footer garis sidebar |  |  | alfon
| bug on datepicker klik field tanggal addlhp |  | done
| css upload addlhp |  | done
| panah atas bawah di datatable |  |  | alfon
| bootstrap loading gif when load url |  |  | alfon |  |  | http://stackoverflow.com/questions/16531234/bootstrap-modal-loading-content-via-remote-url-wait-for-modal-to-fully-load-con
| modal dialog remote edit / view user |  |  | alfon
| datatables manus.php |  | done | alfon
| upload |  | done | alfon
| bug button |  | done | alfon
* review client
* user / admin
tombol detail periode tindak lanjut ganti detail

## coding
create php check if date and auto re format

## clear
| Database blaba | Logo
Copyright
sdfsdf