## TLHP
TLHP |  | status | assignment | desc | link
| Repair User password add edit add repassword | done |  | require re pass if pass input in edit
| Insert Kode Sebab, Uraian, Temuan | progress
| User Authentication | done
Bug ON after add tr rekomen / add more get from last so inputan nya masi ke bawa
Cetak Print
Export to Excel
| kklhp add row temuan | progress
| kklhp add row rekomendasi | progress
| kklhp insert to db | progress
Edit LHP Menu
call reprosess after insert / update manus datatable
Add tim coding post
add tim disable double
datatable get manus
| ci tlhp | done
| ci dashboard | done
datepicker style hover and active
| modal for add user | done | agus
| modal for edit user | done | agus
| data table | done
| Electronic follow up recommendation (index.php) & RB | done
index dashboard tlhp legend on pie chart for printing
| footer add logo kemenpan | done
print dashboard layout
menu layout addlhp fix width & height
menu addlhpbaru tgl penugasan & skop pemeriksaan tidak dapat lebih muda dari surat tugas
addlhpbaru ganti upload laporan
| addlhp all require | done
kklhpbaru tambah A. Sistem, B. Kepatuhan tombol tambah
kklhpbaru kode rekomendasi dropdown chain sub kelompok
kklhpbaru checkbox kerugian negara
kklhpbaru kode sebab muncul kan uriaian text nya
tambah setelah unit kerja nama ppk & PJ Kegiatan
kklhp tambah tombol apabila tindak lanjut
CSS
button print halaman kklhp
button to pdf halaman kklhp
button to excel kklhp
halaman laporan
font muly download ke local
| hari penugasan perpanjangan kolum date nya tidak sama |  | alfon
| header make smaller |  | alfon
| dashboard app make like |  | alfon |  | http://demos.creative-tim.com/paper-dashboard-pro/examples/dashboard/overview.html
| bug datetime picker no hover an active date |  | alfon
| bug on footer garis sidebar |  | alfon
| bug on datepicker klik field tanggal addlhp | done
| css upload addlhp | done
| panah atas bawah di datatable |  | alfon
| bootstrap loading gif when load url |  | alfon |  | http://stackoverflow.com/questions/16531234/bootstrap-modal-loading-content-via-remote-url-wait-for-modal-to-fully-load-con
| modal dialog remote edit / view user |  | alfon
| datatables manus.php |  | alfon
| upload |  | alfon
| bug button |  | alfon
* review client
* user / admin
tombol detail periode tindak lanjut ganti detail

## coding
create php check if date and auto re format